## ExpeditionStories - MVP Reqs
Phase 1
# | Features | App Screen | Platforms | # | MileStones | Hours | Days | Start Date | Delivery Date | Cost
Milestone 1 - Basic POC |  |  |  | 1 | Milestone 1 | 80 | 10 | 2019-02-19 | 2019-03-01 | 500
1 | Mobile Application Start/Stop Trip | Core | Xamarin Native | 2 | Milestone 2 | 144 | 18 | 2019-03-01 | 2019-03-19 | 1200
2 | List of places visited by users during a trip and time spent at each place | Core | Xamarin Native | 3 | Milestone 3 | 192 | 24 | 2019-03-19 | 2019-04-12 | 1500
3 | Categorize places visited as Landmark, Dining, Travel, Lodging, Shopping, Entertainment and Others using location API | Core | Xamarin Native | 4 | Milestone 4 | 144 | 18 | 2019-04-12 | 2019-04-30 | 1200
Milestone 2 |  |  |  | 5 | Milestone 5 | 80 | 10 | 2019-04-30 | 2019-05-10 | 600
4 | User portal UX Design | All | Designing |  | Total | 640 | 80 |  |  | 5000
5 | Prepare Database Design | All | Database
6 | Required Web Services Developments | All | WebService
7 | App and database hosting setup, CI/CD (AWS, Google or Azure) | All | AWS
8 | Authentications(Login/Registration/Forgot Password/FB,Google and Instagram Login | Login | Xamarin Native
9 | Settings (Change Password, About, Contact, Notification, Terms and Conditions, Trip share setting, Feedback/Contact) | Settings | Xamarin Native
10 | Profiles Page (Name, Address, other details) | Profile | Xamarin Native
11 | My Trips(Listing/Edit/Delete) | My Trips | Xamarin Native
12 | Trip View, Landmarks View, Dine View, Lodge View, Map View, Memory View, Travel View | Trip Details | Xamarin Native
13 | Add personal and shared notes to each place logged | Trip Details | Xamarin Native
14 | Testing Implemented Flow | All | QA
Milestone 3
15 | Share Trips | Trip Details | Xamarin Native
16 | Home Screen (Global Shared Trips by other users) | Shared Trips | Xamarin Native
17 | Add/Edit/Delete - Places/Memories(media, notes) inside trip | Trip Details | Xamarin Native
18 | Review-Rating - Trip/Place | Trip Details | Xamarin Native
19 | View trip in private/shared mode | Trip Details | Xamarin Native
20 | Trip Search by Author, Name, Type, Location, Time Period, Dietary Preference, Age Group, Gender, Nationality, Display Picture, Bio | Search Trips | Xamarin Native
21 | Display steps, stairs, miles covered, total places visited info on the trip page | Trip Details | Xamarin Native
22 | Required Web Services Developments | All | WebService
23 | In-app calling for local emergency, saved contact | My Trips | Xamarin Native
24 | Testing Implemented Flow | All | QA
Milestone 4
25 | Admin portal UX Design | All | Designing
26 | Admin role and access control | Admin Console | Xamarin Native
27 | User Managements/Configurations | Admin Console | Xamarin Native
28 | Trips Managements | Admin Console | Xamarin Native
29 | Image, fonts, layout management | Admin Console | Xamarin Native
30 | Testing Implemented Flow | All | QA
Milestone 5
31 | Tutorial/Informative Pages | Settings | Xamarin Native
32 | Notifications/Emails | All | Xamarin Native
33 | User feedback, suggestions and complaints | Feedback | Xamarin Native
34 | User future features ratings | Feedback | Xamarin Native
35 | Required Web Services Developments | All | WebService
36 | Testing Implemented Flow | All | QA
37 | App design, build and QA documentation, well formatted and commented code files | All | Support
38 | Post-launch support and bug fixes (30 days) | All | Support
Formulas:
Delivery Date = [Start Date]+[Days]
Start Date = [Delivery Date, row above]

## Detailed Reqnts
ID | Milestone | Labels | Description | Status
1 |  | Sign Up | User should be able to sign up with a email(username)/password
2 |  | Sign Up | User password should be of of the length and combination considered as secure in industry standards
3 |  | Sign Up | User password should be stored in hidden on input, encrypted on the transit and at rest all the times
4 |  | Sign Up | User should be able to sign up using Google sign up
5 |  | Sign Up | User should be able to sign up using Facebook sign up
6 |  | Sign In | User should be able to sign in using their login information: email(username)/password, Google or FB
7 |  | Sign In | User should be able to recover forgotten password by email verification
8 |  | Sign In | User should be able to change their password if chosen
9 |  | Sign Up | User should NOT be able to create another login using the same email
10 |  | Sign Up | User should be able to access "Terms and Conditions" via a link on the signup page
11 |  | Sign Up | User should accept or agree to "Terms and Conditions" before able to complete the signup
12 |  | Profile Page | User should be able to save following information on the Profile Page - Name (R) - Email (R, grayed out) - Display Name (O) - Home Address (O) - City (O) - State (O) - Country (O) - Gender (O) - Age Group (O) - Nationality (O) - Dietary Preference (O) - Bio (O) - Display Picture (O)
13 |  | Profile Page | User should be able to change all information on their profile EXCEPT the email
14 |  | Profile Page | User should be able to choose any display picture from their phone or saved under their stories
15 |  | Profile Page | User should NOT be allowed to upload restricted picture in their display picture
16 |  | Profile Page | Following fields will have a dropdown to select from in the Profile Page - City - State - Country - Gender - Age Group - Nationality - Dietary Preferences
17 |  | Profile Page | Bio section will be a free text section of 1000 chars
18 |  | Profile Page | User should NOT be able to put restricted words in the bio section
19 |  | Profile Page | State dropdown will be filtered by the Country selection
20 |  | Profile Page | City dropdown will be filtered by the State selection
21 |  | Profile Page | User should be able to select "Others" in the city list and should be able to input a city name if "Others" is selected
22 |  | Settings Page | User should be able to turn default sharing on or off
23 |  | Settings Page | User should be able to turn notifications on or off
24 |  | Settings Page | User can set a default contact whom he/she will be able to call while traveling when needed
25 |  | Settings Page | User should be able to change their password if chosen
|  | Settings Page | User should be able to access "Terms and Conditions" via a link on the Settings page
|  | Settings Page | User should be able to access "About Us" via a link on the Settings page
|  | My Stories Page | User should be able to access Profile and Settings page
|  | My Stories Page | User should be able to create a new trip if no trip is in progress
|  | My Stories Page | User will see their favorite trips at the top. Random 5 favorited trips will be left/right swipeable
|  | My Stories Page | If there is an in progress trip, user will see that trip at the top followed by Favorite trips section
|  | My Stories Page | Under Favorited trip, user will see all their recorded trips in chronological order
|  | My Stories Page | If there are no recorded trips for the user, user will see a default gif/picture
|  | My Stories Page | User should be able to search or filter trips. Clicking on Search button will take them to a Search pop-up
|  | My Story Tile | Each story tile recorded by the user will have following information - Default high resolution photo of the trip city or primary trip city (if trip is across cities) - Trip name provided by the user - Trip duration dates - Trip type provided by the user - Like and view for that trip
|  | My Story Tile | Default location photo for the tile will be managed by the admin and dynamically pulled by the application based on trip primary location
|  | My Story Tile | Font and color for the trip name and dates will be managed by the admin and dynamically pulled by the app
|  | My Story Tile | Trip type icon will be displayed on the top-right corner of the tile
|  | My Story Tile | Trip views and likes will be displayed on the bottom-right corner of the tile
|  | My Story Tile | Trip name and duration will be displayed at location managed by the admin and will be dynmically set by the app
|  | My Story Page | At the footer, user can switch between "My Stories" and "Share Stories" page
|  | My Story Tile | Trip Details page will open when user will click on the Trip tile center or the Trip name area

## ExpeditionStories -Phase 2 Reqs
Phase 2
Milestone TBD |  |  |  | # | MileStones | Hours | Timeline (In Weeks) | Cost
# | Features | App Screen | Platforms | 1 | Milestone 1
1 | Web portal layout for the user - replicate the app experience on web | Web |  | 2 | Milestone 2
2 | Ability to generate a blog |  |  | 3 | Milestone 3
3 | Share the blog or trip on social platform |  |  | 4 | Milestone 4
4 | Ability to search places at a location | App
5 | Email at the trip completion with interesting trip details (timelines, places, etc) | App
6 | Invite trip companions to join and/or edit your trip